## Sheet1
Project Delivery Timeline
Sl No: | Process Name | Acitvity/Task | Timelines(Days)
1 |  | 1.1 - Requirement gathering and Documentation | 5
1.2 - Development
|  | 1.2.1 - Initial Data Retreival | 2
|  | 1.2.2 - Underwriting | 12
|  | 1.2.2.1 - Underwriting New Business | 7
|  | 1.2.2.2 - Underwriting Renewal | 5
|  | 1.2.3 - Debit Payment | 7
|  | 1.2.4 - Cash Receipt | 7
|  | 1.3 - Intregation Testing | 2
|  | 1.3 - UAT | 7
|  | 1.3 - Go Live | 1
|  | Total | 55